## Faculty-Class Match Backlog
ID | User Story | Criteria | Priority | Status | Progress Tracker
EPIC 1: Core Faculty Preference System (MVP) |  |  |  |  | Status | Count
1.1 | Faculty login using college password | Login per college; invalid shows error; no individual accounts | High | Completed | Not Started | 1
1.2 | Term selection with dynamic course list | Dropdown term populates course list | High | Completed | Ongoing | 4
1.3 | Rate courses 0–4 | Ratings validated and saved | High | Completed | Completed | 17
1.4 | Store faculty preferences | Saved to CSV or SQLite | High | Completed
1.5 | Submit preferences | Submit button validates and confirms | High | Completed
EPIC 2: Solver Integration
2.1 | Admin triggers solver | Button runs backend and generates Excel | High | Completed
2.2 | Generate Python solver script | Hard/soft constraints encoded | High | Completed
2.3 | Export Excel results | Downloadable solution.xlsx | High | Completed
EPIC 3: Admin Review & Data Management
3.1 | Download faculty preferences | Export pre-solver preferences via pandas | High | Completed
3.2 | View solver output page | Table showing assignments; re-run solver option | Medium | Not Started
3.3 | Handle crosslisted courses | 470/570 treated as one | Medium | Completed
EPIC 4: Deployment & Hosting
4.1 | Host app on DSU domain | App resolves on bim.inclass.today | Medium | Ongoing
4.2 | GitHub CI validation | Linting and validation on push | Low | Completed
4.3 | Add Testing Framework | Automated tests run on js, html, and python | High | Ongoing
EPIC 5: Quality & Maintenance
5.1 | Avoid feature creep | No new features without approval | Critical | Ongoing
5.2 | Documentation updates | README and comments updated each sprint | High | Ongoing
5.3 | Version control on GitHub | All assets tracked with branch naming conventions | High | Completed
EPIC 6: Bringin it Home
6.1 | Add tests | Tests for python, javascript, and html Code coverage | Medium | Completed
6.2 | Reflections Paper | 3 page paper with inputs from everyone | High | Completed
6.3 | Peer Reviews | Submission of peer review from everyone. NO AI | Medium | Completed
6.4 | Create Slide Deck | Any slides necessary to describe project for final presentation | High | Completed
6.5 | Create Final Presentation | Final presentation/ slide deck/ video of working project | Critical | Completed

## Sprint1
d | User Story | Criteria | Priority | Status | Story Points | Assignee |  | Points Status
1.1 | Faculty login using college password | Login per college; invalid shows error; no individual accounts | High | Completed | 4 | Ryan | Not Started | 0
1.2 | Term selection with dynamic course list | Dropdown term populates course list | High | Completed | 3 | Phoenix | Ongoing | 0
1.3 | Rate courses 0–4 | Ratings validated and saved | High | Completed | 4 | Phoenix | Completed | 19
1.4 | Store faculty preferences | Saved to CSV or SQLite | High | Completed | 4 | Phoenix
1.5 | Submit preferences | Submit button validates and confirms | High | Completed | 4 | Phoenix
Sprint Story Points Total | 19

## Sprint2
ID | User Story | Criteria | Priority | Status | Story Points | Assignee |  | Points Status
2.2 | Generate Python solver script | Hard/soft constraints encoded | High | Completed | 6 | Ryan | Not Started | 0
2.1 | Admin triggers solver | Button runs backend and generates Excel | High | Completed | 4 | Phoenix | Ongoing | 0
2.3 | Export Excel results | Downloadable solution.xlsx | High | Completed | 3 | Ryan | Completed | 18
3.1 | Download faculty preferences | Export pre-solver preferences via pandas | High | Completed | 3 | Andy
4.2 | GitHub CI validation | Linting and validation on push | Low | Completed | 2 | Andy
| Add testing framework | Test framework to run automated tests added | High |  |  | Andy
Sprint Story Points Total | 18

## Sprint3
ID | User Story | Criteria | Priority | Status | Story Points | Assignee |  | Points Status
3.2 | View solver output page | Table showing assignments; re-run solver option | Medium | Not Started | 4 | Phoenix | Not Started | 4
3.3 | Handle crosslisted courses | 470/570 treated as one | Medium | Completed | 3 | Phoenix | Ongoing | 9
4.1 | Host app on DSU domain | App resolves on bim.inclass.today | Medium | Ongoing | 4 |  | Completed | 6
5.1 | Avoid feature creep | No new features without approval | Critical | Ongoing | 2 | ALL
5.2 | Documentation updates | README and comments updated each sprint | High | Ongoing | 3 | ALL
5.3 | Version control on GitHub | All assets tracked with branch naming conventions | High | Completed | 3 | Zack
Sprint Story Points Total | 19

## Sprint4
ID | User Story | Criteria | Priority | Status | Story Points | Assignee |  | Points Status
6.1 | Add tests | Tests for python, javascript, and html added were applicable. Code coverage metric increased | Medium | Completed | 6 | Zack | Not Started | 0
6.2 | Reflections Paper | 3 page paper with inputs from everyone of what went well and what could have been improved | Medium | Completed | 4 | ALL | Ongoing | 0
6.3 | Peer Reviews | Submission of peer review from everyone. NO AI | Medium | Completed | 2 | ALL | Completed | 20
6.4 | Create Slide Deck | Any slides necessary to describe project for final presentation | Critical | Completed | 2 | ALL
6.5 | Create Final Presentation | Final presentation covering slide deck and video of working project | High | Completed | 6 | ALL
Sprint Story Points Total | 20